## Roadmap
PAARAL — Production Roadmap
E-CAIR for the Government Assistance and Subsidies Service (GASS), Department of Education ¦ Version 1.0 ¦ May 2026
THREE VIEWS: WHAT IS NEEDED AND WHEN
View | Current Status | Needed for Jan 2027 Pilot? | Target Timeline | Rationale
Student View | Mockup complete (~100% UI) | YES — Required | January 2027 | The pilot is student-facing; this is the primary deliverable.
School Portal (basic) | Not started | YES — Required | January 2027 | Schools need to see applications and confirm placements. Without this, pilot coordination is unmanageable.
DepEd Planning View | Mockup ~90% done | NO — Deferred to 2028 | National Rollout (2028) | Requires real BigQuery data at national scale. GASS monitors pilot via aggregate reports and CSV exports.
PRODUCTION ROADMAP (May 2026 → 2028)
⚠️ CRITICAL: GASS FY 2027 budget proposal to DBM is typically due July – August 2026. Phase 0 milestone must be reached before then.
Phase | Period | Owner | Key Activities | Milestone / Go-Live Signal
Phase 0 — Mockup Finalization & Sign-Off | May – June 2026 | E-CAIR | • Complete DepEd Planning View mockup (final chunk: deployment + edge cases) • Design school portal wireframes • Stakeholder demo to GASS — sign off on all three view concepts • Jointly define pilot scope with GASS: target divisions, school count, learner cohort • Produce budget estimates for DBM submission ← THIS DOCUMENT | GASS formally endorses UI/UX approach and confirms pilot scope.
Phase 1 — Production Build: Student View + School Portal | July – September 2026 | E-CAIR | • Real LRN validation via DepEd EBEIS API (or agreed data-sharing mechanism) • School/slot data ingestion from GASS records • Persistent wishlist and submission backend • School portal: application inbox, accept/waitlist/decline controls, slot dashboard, CSV export • Staging environment on GCP asia-southeast1 (Firebase + Cloud Run + Cloud SQL) | End-to-end flow functional in staging: student submits → school sees application → school confirms.
Phase 2 — Internal Pilot | October 2026 | E-CAIR + GASS | • Deploy to E-CAIR team + select GASS staff + invited school admin contacts • End-to-end testing with pilot school data (real or anonymized) • Collect structured usability feedback (forms + interviews) • Iterate rapidly (2–3 sprint cycles) • Finalize pilot school list, learner eligibility criteria, communication plan | Internal sign-off that system is ready for external pilot. Go/no-go decision.
Phase 3 — Pilot Preparation | November – December 2026 | E-CAIR + GASS | • Onboard pilot schools (real slot data, school admin accounts created) • Student-facing outreach (DepEd information drive to eligible Grade 6 learners) • School admin training (live sessions + recorded walkthroughs) • Production environment setup (separate from staging) • GASS monitoring dashboard (submission count, slot fill rate, participation rate) • Helpdesk protocol finalized (who handles school vs. student issues) | Pilot schools confirmed and onboarded; students notified; system in production.
Phase 4 — January 2027 Pilot ★ | January – June 2027 | GASS-led, E-CAIR support | • Student-facing enrollment window opens (aligned with Grade 6 SY transition timeline) • Real-time monitoring by E-CAIR + GASS • E-CAIR provides break-fix support under soft deployment SLA • Post-pilot data collection: slot fill rates, rank distribution, school participation, student feedback | Pilot completes. Data collected for sustainability plan. Go/no-go for national rollout.
Phase 5 — Infrastructure Turnover + Sustainability Plan | June – December 2027 | E-CAIR → GASS / DepEd | • E-CAIR produces sustainability plan (system architecture, operational runbook, vendor contracts) • DepEd ICTS or contracted vendor provisions national infrastructure (DICT cloud or GCP) • Codebase, data, and domain transferred to DepEd ownership • E-CAIR provides knowledge transfer under paid support contract • DepEd Planning View development begins (BigQuery integration + real ILP optimizer) | Full ownership transfer complete. National rollout planning underway.
Phase 6 — National Rollout | 2028 onward | DepEd / GASS | • National student view rollout (all ESC-eligible Grade 6 learners) • Full school portal (all ESC-accredited private JHS) • DepEd Planning View in production (real ILP optimization on actual student flow data) • BigQuery analytics pipeline live | Full national deployment. PAARAL operational at scale.

## Budget
PAARAL — Budget Breakdown for Stakeholder Planning
Prepared by E-CAIR for GASS, DepEd Central Office ¦ May 2026 ¦ Pilot scaled to 1,000,000 learners ¦ Exchange rate: ₱62 / USD (BSP reference May 1, 2026: ₱61.42 / USD)
ASSUMPTIONS
Parameter | Value | Description |  |  | Notes
Exchange rate | ₱62 / USD | Conservative planning rate for 2027 appropriation. |  |  | BSP reference May 1, 2026: ₱61.42/USD. Slight weakening factored in.
GCP Region | asia-southeast1 | Singapore — nearest GCP region to the Philippines. |  |  | Cloud Run free tier applies in US regions only. Not applicable here.
Architecture | Firebase + Cloud Run + Cloud SQL + BQ | Firebase Hosting (frontend), Cloud Run (API), Cloud SQL PostgreSQL (database), BigQuery (analytics), Firebase Auth. |  |  | Single GCP account. Shared IAM, billing, no cross-cloud networking costs.
Pilot Scale | 1,000,000 learners | ~33K learners/day avg; ~165K on peak deadline day; ~15M API requests/month during 30-day enrollment window. |  |  | Final scope confirmed jointly by E-CAIR and GASS in Phase 0.
Student Accounts | None (LRN-based, stateless) | No Firebase Auth account created per learner. Students identify via LRN; submissions stored in Cloud SQL keyed by LRN. Only school admins (~100–500 users) have accounts. |  |  | Adding per-learner Firebase Auth accounts would cost ~₱324,000/month during enrollment (950K MAU × $0.0055). Architecture decision confirmed for pilot.
DBM Deadline | July – August 2026 | ⚠️ FY 2027 budget proposals to DBM typically due this window. This document supports that submission. |  |  | GASS must finalize and submit estimates within ~10 weeks of this document.
Concurrency Limit (2027 Pilot) | Max ~20,000–30,000 simultaneous submitting users | ⚠️ The 2027 pilot infrastructure (Cloud SQL 2 vCPU + PgBouncer) handles ~2,000–3,000 API calls/second sustained. This translates to ~20,000–30,000 users actively submitting at the exact same second. All 1M submissions can be processed if spread over at least 2 hours of active enrollment. The system does NOT support all 1M learners submitting simultaneously. |  |  | Mitigation: stagger enrollment access by DepEd division or region. Avoid a single national deadline that creates simultaneous pressure. Set rolling deadlines (e.g., Region I: Jan 15, NCR: Jan 17, Region IV-A: Jan 19). The 2028 national rollout requires a database upgrade (Cloud Spanner or Cloud SQL 16+ vCPU) to remove this constraint.
2026 — E-CAIR SOFT DEPLOYMENT (No cost to GASS)
E-CAIR shoulders all development and hosting costs as an R&D and partnership investment. GASS cost = ₱0 for 2026.
Cloud Compute and Storage Services | Unit Cost | Specs | Qty | Amount | Notes | Purpose
Developer time (Paula + team) | — | Full-stack development: React frontend, Python/Node API, Cloud SQL schema, GeoJSON data layer, school portal. | — | Internal | E-CAIR R&D investment. Not charged to GASS. | Builds the production Student View, School Portal, backend API, and data pipeline — the core deliverable of the soft deployment commitment.
Firebase Hosting — staging | ₱0/month | Static hosting; <100 MB/day transfer; 10 GB storage; Firebase free tier. | 12 | ₱0 | Within 360 MB/day free tier at staging traffic. | Hosts the staging environment where E-CAIR tests features and GASS previews the system before production launch.
Cloud Run — staging backend API | ₱0–310/month | asia-southeast1; <10K req/month (dev traffic); single instance; 0.25 vCPU; 256 MB RAM. | 12 | ₱0–3,720 | Minimal staging traffic; near free tier levels. | Runs the backend API in staging for integration testing and GASS demonstrations. Mirrors production architecture at development traffic levels.
Cloud SQL for PostgreSQL — staging | ₱1,860/month | 1 vCPU, 3.75 GB RAM; 10 GB SSD ($0.222/GB/month); asia-southeast1; no high-availability. | 12 | ₱22,320 | Smallest production-grade instance. No free tier for dedicated Cloud SQL. | Stores test and synthetic data during development. Allows E-CAIR to validate database schema, queries, and data integrity before the January 2027 pilot.
Cloud Storage — static assets, GeoJSON | ₱62/month | Standard storage; <5 GB; $0.020/GB/month; asia-southeast1. | 12 | ₱744 | School coordinate data, GeoJSON boundary files, synthetic datasets. | Hosts school geographic data and map assets used by both the API and the frontend during development and staging.
Firebase Authentication | ₱0/month | Free tier: 50,000 MAU/month. Staging school admin accounts only. | 12 | ₱0 | Within 50,000 MAU free tier. | Manages school admin accounts in the staging environment for internal testing and GASS demonstrations.
Domain registration | ₱1,500/year | .ph domain (dotPH registry) or ecair.ph subdomain. SSL/TLS via Firebase Hosting (no extra cost). | 1 | ₱1,500 | paaral.ph or paaral.ecair.ph. | Establishes the public URL for PAARAL. Required before the pilot goes live — students and schools need a stable, recognizable address to access the system.
TOTAL GASS COST FOR 2026 |  |  |  | ₱0 | E-CAIR investment — all costs absorbed by E-CAIR.
E-CAIR out-of-pocket for 2026: ~₱26,000 – ₱30,000 in GCP costs + developer time (internal).
2027 — GASS PILOT BUDGET (FY 2027 DBM Proposal — MOOE) ¦ Scaled to 1,000,000 Learners
Budget Category: MOOE. Enrollment window: 30 days (January 2027). Peak: ~165K learners/day; ~15M API requests/month. Unit Cost = average monthly PHP. Qty = 12 months.
A. Cloud Compute and Storage Services (Google Cloud Platform, asia-southeast1)
Cloud Run free tier (2M req/month) applies in US regions only — does NOT apply in asia-southeast1. Firebase Hosting and Auth free tiers apply globally. Enrollment window: 90 days (Jan–Mar 2027).
Cloud Compute and Storage Services | Unit Cost | Specs | Qty | Amount | Notes | Purpose
Firebase Hosting (Student View) | ₱55,800/enrollment | Global CDN; React app shell (~80 KB gzipped) + schools.json (60,421 schools, 16 fields, ~6 MB gzipped). ~6 TB total bandwidth during enrollment (1M unique learners × ~6 MB). Blaze plan. Storage <1 GB. | 1 enrollment | ₱55,800 | 6,000 GB × $0.15/GB = $900 = ₱55,800. Cost is incurred almost entirely during the enrollment window — ~₱0 off-season. schools.json cached after first load; cost reflects 1M unique first-time visitors. | Delivers the Student View to learners' browsers. The dominant transfer cost is schools.json — a pre-built static file of all 60,421 Philippine schools (16 fields, ~6 MB gzipped) loaded once per learner. All school search and filtering runs client-side with no API calls.
Firebase Hosting (School Portal) | ₱0/month | Global CDN; React app shell (~80 KB gzipped) only. ~500 school admins × 80 KB = ~40 MB total bandwidth for the year. Well within 360 MB/day free tier. | 12 months | ₱0 | School admin traffic is negligible — ~500 admins vs 1M learners. Free tier (360 MB/day) is never approached. | Delivers the School Portal to school administrators' browsers. Admins review incoming student applications, confirm or decline placements, and export enrollment data. No large static data file needed — all applicant data is fetched from the API per school.
Firebase Authentication | ₱0/month | Free tier: 50,000 MAU/month. Only school admins (~100–500 users) have Firebase Auth accounts. Students use stateless LRN validation — no Firebase Auth account created per learner. | 12 months | ₱0 | Budget assumes NO per-learner accounts. If added in future: ~₱324,000/month during enrollment (950K MAU × $0.0055). | Secures the School Portal — only verified school administrators can view student applications and manage slot confirmations. Students are identified by LRN only; no learner login is required.
Cloud Run (Student View API, asia-southeast1) | ₱3,500/enrollment | ~3.5M total API requests during enrollment window: LRN validation (1M), draft saves (1.5M), final submissions (1M). min-instances: 1 for 90-day window; max-instances: 50. 1 vCPU (required — Cloud Run enforces max 1 concurrent request per instance for <1 vCPU); 256 MB RAM. | 1 enrollment | ₱3,500 | Rates: CPU active $0.0000336/vCPU-sec, CPU idle $0.0000035/vCPU-sec, Memory $0.0000035/GiB-sec, Requests $0.40/M (asia-southeast1, no free tier). Breakdown: CPU active 700K vCPU-sec × $0.0000336 = $23.52; CPU idle 7.08M vCPU-sec × $0.0000035 = $24.77; Memory active+idle = $6.80; Requests 3.5M × $0.40/M = $1.40. Total ~$56.50 = ₱3,502 → ₱3,500. Schools.json is served by Firebase Hosting — not Cloud Run. Scales to zero off-season. | Handles every transactional action for learners: LRN validation against DepEd EBEIS, saving draft ranked choices, and final submission of applications. School browsing requires no API call — served from the static schools.json file loaded on app open.
Cloud Run (School Portal API, asia-southeast1) | ₱100/enrollment | ~100K total API requests during enrollment window: view applicants, confirm/decline, slot dashboard, CSV export. ~500 school admins × ~200 actions. 0.25 vCPU; 256 MB RAM. min-instances: 0 (cold starts acceptable for admin workflow). | 1 enrollment | ₱100 | Rates: CPU active $0.0000336/vCPU-sec (asia-southeast1). Breakdown: CPU active 100K × 0.2s × 0.25 vCPU × $0.0000336 = $0.17; Memory = $0.02; Requests 100K × $0.40/M = $0.04. Total ~$0.23 = ₱14. Rounded to ₱100 for contingency. School Portal admin traffic (500 users) is negligible vs. Student View (1M learners). Scales to zero off-season. | Handles all School Portal actions: loading the ranked-choice applicant list per school, processing accept/decline/waitlist decisions, updating slot counts, and generating CSV exports of confirmed enrollees for GASS records.
Compute Engine e2-standard-2 (OSRM road routing server) | ₱5,736/month | 2 vCPU, 8 GB RAM; asia-southeast1; $0.0767/hour on-demand. Runs for 90-day enrollment window only; shut down off-season. Hosts OSRM with Philippines OSM road network (~3 GB loaded in memory). | 3 months | ₱10,272 | $0.0767/hour × 2,160 hrs (90 days) = $165.67 = ₱10,272. Compute Engine required — Cloud Run cannot hold the 3 GB road network in memory persistently (cold starts take 30–60 sec loading the routing graph). Compute Engine source: cloud.google.com/compute/all-pricing. | Self-hosted road routing engine. Computes road distance (km) and estimated travel time between a learner's location and each school they view in detail. Using OSRM (open-source, free) instead of Google Maps Distance Matrix API saves ~₱3,100,000 (Google Maps would cost $5 per 1,000 pairs × 10M pairs for 1M learners × 10 school views).
Cloud SQL for PostgreSQL (2 vCPU, 7.5 GB RAM) | ₱9,247/month | 2 vCPU, 7.5 GiB RAM; 50 GB SSD; asia-southeast1; always-on. Enterprise Edition — General Purpose. Rates: $0.0578/vCPU/hr + $0.0098/GiB/hr + $0.222/GB/month SSD. | 12 months | ₱111,000 | vCPU: 2 × $0.0578 × 730 = $84.39/mo. Memory: 7.5 GiB × $0.0098 × 730 = $53.66/mo. Storage: 50 GB × $0.222 = $11.10/mo. Total: $149.15/mo × 12 × ₱62 = ₱110,960 → ₱111,000. Source: cloud.google.com/sql/pricing [Source 3]. | The authoritative database for all pilot data: student ranked-choice submissions keyed by LRN, ESC slot allocations from GASS, school admin accounts, and enrollment audit logs. Persists data year-round across enrollment windows.
Cloud SQL Automated Backups (90-day retention) | ₱620/month | 90-day automated daily backup retention; PITR enabled; ~110 GB backup storage at steady state (90 compressed snapshots × ~1 GB + WAL logs); $0.08/GB/month. | 12 months | ₱7,440 | Cloud SQL built-in — no separate product. Extends default 7-day retention to 90 days via Cloud SQL settings. | Protects student submission data against accidental deletion or system failure. Enables full recovery to any point within 90 days — covering the enrollment window plus a post-close period for dispute resolution, as required for government enrollment records.
PgBouncer (connection pooler, Cloud Run service) | ₱620/month | Lightweight pooler as a permanent Cloud Run service; min-instances: 1. Routes Cloud Run instances through a shared pool of 20–30 DB connections. | 12 months | ₱7,440 | Required at 1M learner scale. Without it, 100+ Cloud Run instances × 5 connections = Cloud SQL exhaustion. | Allows Cloud Run to auto-scale to 100+ instances without crashing the database. Acts as a traffic manager between the API and Cloud SQL — critical for handling the deadline-day enrollment burst without service interruption.
Cloud Run Jobs (ILP optimization engine) | ₱155/month | Async batch compute for OR-Tools / PuLP optimization runs. 2 vCPU, 8 GB RAM per job; ~30–60 min per run. Invoked by GASS planning staff. | 12 months | ₱1,860 | ~$0.12/run; estimated 10 runs/month max. Async — avoids Cloud Run's 60-min HTTP timeout. | Runs GASS's ESC slot allocation optimization scenarios as background batch jobs, separate from the student-facing API. Ensures heavy computation (30–60 min) does not affect student enrollment availability or response times.
Cloud Storage (GeoJSON, school data files) | ₱310/month | Standard storage; school coordinates, GeoJSON boundaries, ESC slot exports; <10 GB; $0.020/GB/month; asia-southeast1. | 12 months | ₱3,720 | Minimal footprint. Costs dominated by Cloud SQL and hosting. | Stores the geographic and school reference data used across the system: school map coordinates, regional boundary files for the Student View map, and ESC slot allocation data exports for GASS.
BigQuery (pilot-scale analytics) | ₱155/month | On-demand queries for GASS reporting; <1 TB queries/month at $6.25/TB. Storage <10 GB at $0.020/GB/month. Free tier: 10 GB storage, 1 TB queries/month. | 12 months | ₱1,860 | Likely within or near free tier at pilot scale. | Provides GASS with aggregate pilot monitoring — total submissions, slot fill rates by school, geographic distribution of applications, and rank preference breakdowns — without querying the live production database and affecting enrollment performance.
Egress, Cloud Monitoring, Secret Manager | ₱620/month | Internet egress ($0.19/GB); Cloud Monitoring (free tier alerting + dashboards); Secret Manager for API keys ($0.06/secret/month). | 12 months | ₱7,440 | Egress driven by API responses to 1M learners during enrollment. | (1) Egress — pays for data transmitted from GCP to learners' devices during enrollment; (2) Cloud Monitoring — alerts E-CAIR and GASS if the system goes down during the enrollment window; (3) Secret Manager — securely stores DepEd EBEIS API credentials so they are never hardcoded in the application.
GCP Subtotal |  |  |  | ₱210,332
GCP Budget (rounded, with ~20% contingency) |  | Contingency covers scope expansion, Firebase bandwidth overrun, or Cloud SQL tier upgrade. |  | ₱255,000 | Recommended DBM line item: Cloud Compute and Storage Services (MOOE).
SCENARIO B — Remove Concurrency Limit (All 1M Learners May Access and Submit Simultaneously)
Scenario A (above) handles up to ~20,000–30,000 simultaneous submitting users and requires staggered access by DepEd division. Scenario B removes this constraint. Only changed line items are shown — all other components (Firebase Hosting, Firebase Auth, PgBouncer, Cloud Run Jobs, Cloud Storage, BigQuery, Egress) remain the same as Scenario A.
Cloud Compute and Storage Services | Unit Cost | Specs | Qty | Amount | Notes | Purpose
Compute Engine (OSRM × 10 instances, load balanced) | ₱102,734/enrollment | 10 × e2-standard-2 (2 vCPU, 8 GB RAM each) behind a Cloud Load Balancer; asia-southeast1. Handles ~5,500 routing queries/second (1M users × 10 school views ÷ 1,800 sec). Runs 90-day enrollment window only. | 1 enrollment | ₱102,734 | 10 × $0.0767/hour × 2,160 hours = $1,657 = ₱102,734. vs. Scenario A: ₱10,272 (1 instance). Additional cost: +₱92,462. Requires Cloud Load Balancer in front of instance group. | Scales the road routing engine from 1 to 10 instances to handle peak concurrent distance queries from all 1M learners browsing simultaneously. Without this, a single OSRM instance saturates at ~1,000 queries/second — insufficient for 1M concurrent users.
Cloud SQL for PostgreSQL (32 vCPU, 120 GiB RAM — enrollment window) | ₱405,129/enrollment + ₱85,317 off-season & storage | db-custom-32-122880; asia-southeast1. Rates: $0.0578/vCPU/hr + $0.0098/GiB/hr [Source 3]. Scaled up for 90-day enrollment window only — downscaled to 2 vCPU off-season. Handles ~1,900 DB writes/second sustained (1M users × 3.5 API calls ÷ 1,800 sec). | 1 year | ₱490,000 | Enrollment 2,160 hrs: (32 × $0.0578 + 120 × $0.0098) × 2,160 = $3.026/hr × 2,160 = $6,534 = ₱405,129. Off-season 9 months (2 vCPU/7.5 GiB): $1,243 = ₱77,066. Storage $0.222/GB × 50 GB × 12 = $133 = ₱8,258. Total: $7,910 × ₱62 = ₱490,446 → ₱490,000. vs. Scenario A: ₱111,000. Additional cost: +₱379,000. Scale-up/down requires planned maintenance window. | Upgrades the database to handle ~1,900 concurrent writes/second — the throughput required when all 1M learners are submitting simultaneously. The 2 vCPU instance in Scenario A caps at ~200–400 writes/second; this 32 vCPU instance removes that bottleneck entirely.
GCP Subtotal — Scenario B |  | (Scenario A unchanged items: ₱210,332 − ₱10,272 OSRM − ₱111,000 Cloud SQL) + ₱102,734 OSRM × 10 + ₱490,000 Cloud SQL 32 vCPU |  | ₱681,794
GCP Budget — Scenario B (rounded, with ~20% contingency) |  | Same contingency buffer as Scenario A. Covers Cloud Load Balancer setup for OSRM and Cloud SQL scale-up/down operational overhead. |  | ₱825,000 | vs. Scenario A: ₱255,000. Additional GCP cost for removing concurrency limit: +₱570,000.
★ SCENARIO B — RECOMMENDED FY 2027 BUDGET ASK (MOOE) |  | Removes the 20,000–30,000 simultaneous user limit. No staggered scheduling required. All 1M learners may access and submit at any time during the enrollment window. |  | ₱3,100,000 | vs. Scenario A: ₱2,500,000. Additional cost: +₱570,000 GCP (Cloud SQL 32 vCPU + OSRM × 10 instances). E-CAIR and Operations components unchanged. | Funds the full pilot with no operational constraints on concurrent access — any learner can submit at any time without risk of system degradation.
B. Professional Services — E-CAIR Maintenance and Support Retainer (12-month)
Scope: break-fix, security patches, minor enhancements, DevOps/monitoring, GASS technical support. ~30–40 hours/month. Subject to E-CAIR's formal proposal.
Service | Unit Cost | Specs | Qty | Amount | Notes | Purpose
Maintenance and support retainer (E-CAIR) | ₱60,000–120,000/month | Bug fixes; security patches; minor feature enhancements; DevOps monitoring and incident response; GASS technical support calls. | 12 months | ₱720,000–1,440,000 | Rate confirmed via E-CAIR's formal proposal. Range based on Philippine IT consulting rates. | Ensures the platform remains operational, secure, and responsive to GASS feedback throughout the pilot year. Provides the technical expertise required to maintain a government-grade enrollment system that 1M learners depend on — covering both routine upkeep and incident response.
C. GASS Operations
Item | Unit Cost | Specs | Qty | Amount | Notes | Purpose
Helpdesk support (contracted, part-time) | ₱15,000–25,000/month | 1 staff handling school admin and student inquiries during pilot enrollment window. Agency or BPO contract. | 12 months | ₱180,000–300,000 | Handles Tier 1 issues. E-CAIR escalation for technical issues. | Ensures school administrators and learners receive timely support during the enrollment window. Without dedicated helpdesk coverage, routine questions (login errors, submission issues, slot queries) would escalate to E-CAIR and delay resolution.
School admin training and onboarding | ₱80,000–150,000 total | Live sessions (in-person or virtual), printed quick-start guides, recorded walkthrough videos, Q&A documentation. | 1 (one-time) | ₱80,000–150,000 | One-time for pilot schools. Will need to scale for national rollout. | Enables school staff to independently operate the School Portal — reviewing student applications, confirming placements, managing slots, and exporting enrollment data. A trained school admin base is a prerequisite to pilot launch; without it, schools cannot participate.
Contingency (10% of total budget) | — | 10% buffer for unexpected scope, additional training rounds, or vendor cost changes. | — | ₱118,000–219,000 | 10% applied to full budget total (GCP + E-CAIR + Operations). | Provides budget flexibility to absorb unexpected costs without requiring a supplemental appropriation — e.g., scope expansion to more schools, additional training rounds, or infrastructure tier upgrades triggered by higher-than-expected traffic.
Operations Subtotal |  |  |  | ₱378,000–669,000
2027 GRAND TOTAL
Category | Unit Cost | Description | Qty | Amount | Notes | Purpose
A. Cloud Compute and Storage Services | ₱255,000/year | Firebase Hosting (schools.json + app shell), Cloud Run (enrollment API), Compute Engine (OSRM routing), Cloud SQL + Backups, PgBouncer, Cloud Run Jobs, Storage, BigQuery, Egress, Monitoring. | 1 year | ₱255,000 | Hard cost; backed by Google official pricing. See Sources. Includes Compute Engine for OSRM road routing server (90-day enrollment window). | Provides the cloud infrastructure that runs the Student View, School Portal, and optimization engine — the technical foundation of the entire pilot.
B. E-CAIR Professional Services | ₱60k–120k/month | 12-month maintenance and support retainer. | 12 months | ₱720,000–1,440,000 | Subject to E-CAIR's proposed rate. | Keeps the system operational and evolving throughout the pilot year, with E-CAIR responsible for technical uptime and GASS able to focus on policy operations.
C. GASS Operations | — | Helpdesk, school admin training, contingency. | — | ₱378,000–669,000 |  | Ensures schools and learners can participate effectively in the pilot — trained admins, supported users, and budget flexibility for the unexpected.
TOTAL |  |  |  | ₱1,353,000–2,364,000
★ SCENARIO A — RECOMMENDED FY 2027 BUDGET ASK (MOOE) |  | Staggered enrollment by DepEd division. Max ~20,000–30,000 simultaneous submitting users. Accommodates upper bound of E-CAIR rates, scope expansion, and training contingency. |  | ₱2,500,000 | GCP: ₱255,000 ¦ E-CAIR: up to ₱1,440,000 ¦ Operations: up to ₱669,000 ¦ Contingency buffer included. | Funds the full production and pilot deployment of PAARAL with staggered access scheduling — enabling DepEd to run a credible, data-backed ESC enrollment pilot for 1 million learners.
★ SCENARIO B — RECOMMENDED FY 2027 BUDGET ASK (MOOE) |  | No staggering required. All 1M learners may access and submit simultaneously. OSRM scaled to 10 instances; Cloud SQL upgraded to 32 vCPU during enrollment window. |  | ₱2,875,000 | GCP: ₱825,000 ¦ E-CAIR: up to ₱1,440,000 ¦ Operations: up to ₱669,000 ¦ Additional vs. Scenario A: +₱570,000 GCP. | Funds the full pilot with no operational constraints on concurrent access — eliminates the need for GASS to coordinate staggered enrollment windows by division.
2028+ — NATIONAL ROLLOUT (Indicative; for Sustainability Plan)
Final amounts depend on national scope (10,000+ schools, 500,000+ learners). To be refined in the sustainability plan after pilot data is available.
Cloud Compute and Storage Services — National Scale
Cloud Compute and Storage Services | Unit Cost | Specs | Qty | Amount | Notes | Purpose
Firebase Hosting (national traffic) | ₱3,100–6,200/month | Exceeds free transfer tier; ~10 GB+/day bandwidth at national scale. | 12 months | ₱37,200–74,400 | CDN-cached but first-load bandwidth scales with unique user count. | Delivers the Student View to all ESC-eligible Grade 6 learners nationwide. CDN distributes the app globally so even learners in Mindanao and Visayas get fast load times.
Cloud Run (national enrollment traffic) | ₱3,100–9,920/month | Millions of req/month during June–July enrollment peak; higher min-instances. | 12 months | ₱37,200–119,040 | Auto-scales with traffic; no VM pre-provisioning. | Handles enrollment requests from all participating schools and learners across all DepEd divisions. Auto-scaling absorbs the June–July Grade 6 enrollment peak without pre-provisioning capacity.
Cloud SQL 16+ vCPU / 60 GB RAM or Cloud Spanner | ₱24,800–49,600/month | Cloud SQL 16 vCPU / 60 GB RAM ($400–600/month) handles ~1,000 concurrent connections. Cloud Spanner (1 node, $648/month) provides unlimited horizontal scaling. Final choice determined by pilot concurrency data. | 12 months | ₱297,600–595,200 | Upgrade required for national-scale concurrent load. 2027 pilot infrastructure (2 vCPU) caps at ~20,000–30,000 simultaneous submitting users — insufficient for national rollout without staggering. Cloud Spanner removes the concurrency ceiling entirely. | Handles concurrent writes from all DepEd regions simultaneously during the national enrollment peak. The 2027 Cloud SQL instance is the binding concurrency constraint for the pilot — this upgrade removes it for national rollout, allowing all learners to submit without staggered scheduling.
BigQuery (Planning View analytics) | ₱6,200–24,800/month | Heavy query volume for DepEd Planning View optimization simulations on full national dataset. | 12 months | ₱74,400–297,600 | On-demand: $6.25/TB. Cost depends on GASS query frequency. | Powers the DepEd Planning View — enabling GASS to run ILP optimization simulations on the full national student flow dataset (29,000+ school-pair flows) for evidence-based ESC slot allocation decisions.
Cloud Storage + CDN | ₱620–1,240/month | School registry, national GeoJSON, ESC slot history; CDN for faster regional delivery. | 12 months | ₱7,440–14,880 | Storage grows slowly; CDN reduces Cloud Run egress costs. | Hosts the complete national school registry and geographic data, and distributes it efficiently to regional offices and school division users via CDN caching.
Egress + Monitoring + PgBouncer | ₱1,550–3,720/month | Higher internet egress at national scale; enhanced monitoring; connection pooling for national load. | 12 months | ₱18,600–44,640 | Monitoring includes alerting across all DepEd divisions. | Sustains national-scale operations: data transfer to all regions, system health monitoring across all DepEd divisions, and database connection management at national concurrent load.
GCP Subtotal |  |  |  | ₱472,440–1,145,760
Full Annual Budget — Indicative (2028)
Category | Unit Cost | Description | Qty | Amount | Notes | Purpose
GCP Infrastructure | — | See GCP table above. Includes Cloud SQL 16+ vCPU or Cloud Spanner for national-scale concurrency. | 1 year | ₱473,000–1,146,000 | Hard infrastructure cost. Cloud SQL/Spanner upgrade is the largest cost driver vs. 2027 pilot. | Provides the cloud foundation for national-scale enrollment, school administration, and GASS analytics across all DepEd regions. Concurrency constraint from 2027 pilot is removed by the database upgrade.
DepEd Planning View development (one-time) | — | BigQuery pipeline + real ILP optimizer (OR-Tools or Gurobi). One-time. | 1 | ₱1,000,000–2,000,000 | May be classified as Capital Outlay (CO) per DBM guidelines. | Builds the production DepEd Planning View with real national data and a mathematical optimizer — enabling GASS to make evidence-based ESC slot allocation decisions rather than relying on estimates or historical patterns.
Platform maintenance contract | — | Larger scope: national school count, full data pipeline, all three views. | 1 year | ₱1,440,000–3,600,000 | E-CAIR long-term contract or DepEd in-house team. | Sustains all three PAARAL views (Student, School, DepEd Planning) at national scale and incorporates feedback from the 2027 pilot — ensuring the system continues to improve after turnover.
Helpdesk + school support operations | — | 2–3 full-time staff or contracted BPO, scaled to national school count. | 1 year | ₱500,000–1,000,000 |  | Provides support coverage for all participating schools and students across all DepEd divisions — ensuring no school is left without assistance during the national enrollment window.
Training + change management (national) | — | Per-division rollout training; printed materials, online guides, live sessions. | 1 year | ₱200,000–500,000 | All DepEd divisions; ~200+ divisions nationwide. | Ensures all DepEd divisions and school administrators can independently use PAARAL without relying on E-CAIR for routine operations — a prerequisite for sustainable national deployment.
2028 ANNUAL TOTAL (indicative) |  |  |  | ₱3,615,000–8,248,000 | To be refined in sustainability plan once pilot data is available. Increase from 2027 driven primarily by database upgrade for national-scale concurrency.
SOURCES
All infrastructure cost estimates are derived from official Google Cloud pricing pages and verified third-party sources. Exchange rate from BSP reference.
# | Source | URL |  | Used to Price
1 | Google Cloud Run Pricing | https://cloud.google.com/run/pricing |  | Cloud Run asia-southeast1 (Tier 2) request-based billing: CPU active $0.0000336/vCPU-second, CPU idle (min-instance) $0.0000035/vCPU-second, Memory active/idle $0.0000035/GiB-second, Requests $0.40/million. Free tier (2M req/month, 180K vCPU-sec, 360K GiB-sec) applies in US regions only — NOT in asia-southeast1.
2 | Google Cloud SQL Pricing — Instance Rates | https://cloud.google.com/sql/pricing |  | Enterprise Edition, General Purpose, asia-southeast1 (on-demand): vCPU $0.0578/vCPU-hour, Memory $0.0098/GiB-hour. CUD 1-year: $0.04335/vCPU-hour, $0.00735/GiB-hour. HA rates are 2× standard. Verified May 2026 from official pricing page.
3 | Google Cloud SQL Pricing — Storage & Egress | https://cloud.google.com/sql/pricing |  | SSD storage: $0.222/GB/month. Backup storage: $0.08/GB/month. Egress: $0.19/GB to internet. No free tier for dedicated instances.
4 | Firebase Pricing | https://firebase.google.com/pricing |  | Hosting free tier: 10 GB storage, 360 MB/day transfer; overage $0.026/GB storage, $0.15/GB transfer. Auth free tier: 50,000 MAU/month; beyond: $0.0055/MAU via Cloud Identity Platform.
5 | Google BigQuery Pricing | https://cloud.google.com/bigquery/pricing |  | On-demand queries: $6.25/TB scanned. Storage: $0.020/GB/month active, $0.010/GB/month long-term. Free tier: 1 TB/month queries, 10 GB/month storage.
6 | BSP / PhilNews — USD/PHP Rate, May 1, 2026 | https://philnews.ph/2026/05/01/usd-to-php-exchange-rate-today-friday-may-1-2026 |  | BSP reference rate: ₱61.42/USD on May 1, 2026. Budget uses ₱62/USD as conservative planning rate for 2027.
7 | Google Compute Engine Pricing | https://cloud.google.com/compute/all-pricing |  | e2-standard-2 (2 vCPU, 8 GB RAM) on-demand price in asia-southeast1: $0.0767/hour. Used to price the OSRM road routing server (90-day enrollment window = 2,160 hours = $165.67 = ₱10,272).
Document prepared by E-CAIR ¦ Contact: paumartinez.work@gmail.com ¦ Prices subject to change; verify on official pricing pages before DBM submission.

## Calculations
PAARAL — Cost Calculation Workbook
Detailed arithmetic behind each Budget tab line item. Exchange rate: ₱62/USD (BSP reference May 1, 2026: ₱61.42/USD). GCP region: asia-southeast1.
1. Firebase Hosting — Student View → Budget tab: ₱55,800 / enrollment
Inputs & Assumptions
Unique learners (pilot scope) | 1,000,000 |  |  | All ESC-eligible Grade 6 learners. Confirmed jointly with GASS in Phase 0.
schools.json size (gzipped) | 6 MB |  |  | Conservative estimate. 60,421 schools × 16 static fields; ~30 MB uncompressed. 6 MB is the conservative gzipped figure.
App shell (gzipped) | ~80 KB |  |  | React bundle (JS + CSS). Negligible vs. schools.json; omitted from calculation.
Firebase Blaze plan — transfer overage rate | $0.15 / GB |  |  | Source: firebase.google.com/pricing [Source 4]
Firebase free tier | 360 MB / day |  |  | Exhausted in minutes on enrollment day (1M learners × 6 MB = 6,000 GB >> 360 MB/day). All bandwidth billed at overage.
Calculation
Component / Parameter | Rate | × Quantity | = USD | Notes / Source
Total bandwidth transferred | $0.15 / GB | 6,000 GB | $900.00 | 1,000,000 learners × 6 MB ÷ 1,000 = 6,000 GB × $0.15/GB
Subtotal (USD) |  |  | $900.00
× ₱62 / USD = | $900.00 | ₱55,800 |  | → Budget tab: "Firebase Hosting (Student View)" = ₱55,800 / enrollment
2. Firebase Hosting — School Portal → Budget tab: ₱0
Inputs & Assumptions
School admins (MAU) | ~500 |  |  | One admin per participating school (~100–500 pilot schools).
App shell per load (gzipped) | 80 KB |  |  | React bundle. No large static file — applicant data fetched from the API per school.
Firebase free tier | 360 MB / day (10 GB / month) |  |  | Applies globally to Firebase Hosting.
Calculation
Component / Parameter | Rate | × Quantity | = USD | Notes / Source
Total bandwidth transferred | $0.15 / GB | 0.04 GB | $0.00 | 500 admins × 80 KB = 40 MB. Free tier = 360 MB/day >> 40 MB total for the year. No billing triggered.
Subtotal (USD) |  |  | $0.00
× ₱62 / USD = | $0.00 | ₱0 |  | → Budget tab: "Firebase Hosting (School Portal)" = ₱0
3. Firebase Authentication → Budget tab: ₱0
Inputs & Assumptions
School admin accounts (MAU) | ~500 |  |  | Only school admins have Firebase Auth accounts. Authentication decision: students use stateless LRN validation — no Firebase Auth account created per learner.
Firebase Auth free tier | 50,000 MAU / month |  |  | Source: firebase.google.com/pricing [Source 4]
Cost if per-learner accounts were added | ~₱324,000 / month during enrollment |  |  | For reference only: 950K MAU × $0.0055/MAU = $5,225/month = ₱324,000/month. Architecture decision to use LRN-only avoids this cost.
Calculation
Component / Parameter | Rate | × Quantity | = USD | Notes / Source
School admin MAU vs. free tier | $0.0055 / MAU (beyond 50K) | ~500 MAU | $0.00 | 500 MAU << 50,000 MAU free tier. No billing triggered.
Subtotal (USD) |  |  | $0.00
× ₱62 / USD = | $0.00 | ₱0 |  | → Budget tab: "Firebase Authentication" = ₱0
4. Cloud Run — Student View API (asia-southeast1, request-based) → Budget tab: ₱3,500 / enrollment
Inputs & Assumptions
Total API requests (enrollment window) | 3,500,000 |  |  | LRN validation (1M) + draft saves (1.5M, avg 1.5 saves per learner) + final submissions (1M). School browsing served from static schools.json — no API call.
Average request duration | 0.2 seconds |  |  | Estimate: DB query via PgBouncer + LRN validation + JSON response. Latency dominated by Cloud SQL round-trip (~100–200 ms).
vCPU allocation | 1 vCPU |  |  | Required: Cloud Run enforces max 1 concurrent request per instance for <1 vCPU. 1 vCPU allows concurrency=80 (multiple requests handled per instance simultaneously).
Memory allocation | 256 MB = 0.25 GiB |  |  | Sufficient for a stateless Node.js/Python API handling LRN validation and DB queries.
Min-instances | 1 (for 90-day enrollment window) |  |  | Keeps 1 warm instance active throughout enrollment. Eliminates cold start latency for learners. Set to 0 off-season.
Enrollment window | 90 days = 7,776,000 seconds |  |  | January – March 2027. The min-instance idle cost accumulates for this entire period.
Derived Values
Total active vCPU-seconds | 700,000 vCPU-sec |  |  | 3,500,000 requests × 0.2 sec × 1 vCPU
Total idle seconds (1 min-instance) | 7,076,000 sec |  |  | 7,776,000 total − 700,000 active = 7,076,000 idle
Total active memory GiB-seconds | 175,000 GiB-sec |  |  | 3,500,000 requests × 0.2 sec × 0.25 GiB
Total idle memory GiB-seconds (min-instance) | 1,769,000 GiB-sec |  |  | 7,076,000 idle sec × 0.25 GiB
Cost Components [Source 1: cloud.google.com/run/pricing — asia-southeast1 Tier 2]
Component / Parameter | Rate | × Quantity | = USD | Notes / Source
Requests | $0.40 / million | 3,500,000 req | $1.40 | No free tier in asia-southeast1 (free tier is US regions only).
CPU — active time | $0.0000336 / vCPU-sec | 700,000 vCPU-sec | $23.52 | 3.5M × 0.2s × 1 vCPU × $0.0000336
CPU — idle (1 min-instance, 90 days) | $0.0000035 / vCPU-sec | 7,076,000 vCPU-sec | $24.77 | (7,776,000 − 700,000) × 1 vCPU × $0.0000035 ← dominant cost: instance runs 24/7 during enrollment
Memory — active time | $0.0000035 / GiB-sec | 175,000 GiB-sec | $0.61 | 3.5M × 0.2s × 0.25 GiB × $0.0000035
Memory — idle (1 min-instance, 90 days) | $0.0000035 / GiB-sec | 1,769,000 GiB-sec | $6.19 | 7,076,000 × 0.25 GiB × $0.0000035
Subtotal (USD) |  |  | $56.49
× ₱62 / USD = | $56.49 | ₱3,502 → rounded ₱3,500 |  | → Budget tab: "Cloud Run (Student View API)" = ₱3,500 / enrollment
5. Cloud Run — School Portal API (asia-southeast1, request-based) → Budget tab: ₱100 / enrollment
Inputs & Assumptions
Total API requests (enrollment window) | 100,000 |  |  | ~500 school admins × ~200 actions each: view applicant list, confirm/decline/waitlist, check slot dashboard, export CSV.
Average request duration | 0.2 seconds |  |  | Same estimate as Student View API.
vCPU allocation | 0.25 vCPU |  |  | Low-traffic service. Concurrency=1 per instance is acceptable — admins are not time-pressured the way students are.
Memory allocation | 256 MB = 0.25 GiB
Min-instances | 0 |  |  | Cold starts (1–3 sec) are acceptable for school admins. No min-instance idle cost.
Derived Values
Total active vCPU-seconds | 5,000 vCPU-sec |  |  | 100,000 × 0.2 sec × 0.25 vCPU
Total active memory GiB-seconds | 5,000 GiB-sec |  |  | 100,000 × 0.2 sec × 0.25 GiB
Cost Components [Source 1: cloud.google.com/run/pricing — asia-southeast1 Tier 2]
Component / Parameter | Rate | × Quantity | = USD | Notes / Source
Requests | $0.40 / million | 100,000 req | $0.04 | No free tier in asia-southeast1.
CPU — active time | $0.0000336 / vCPU-sec | 5,000 vCPU-sec | $0.17 | 100K × 0.2s × 0.25 vCPU × $0.0000336
Memory — active time | $0.0000035 / GiB-sec | 5,000 GiB-sec | $0.02 | 100K × 0.2s × 0.25 GiB × $0.0000035
Subtotal (USD) |  |  | $0.23
× ₱62 / USD = | $0.23 | ₱14 → rounded ₱100 |  | → Budget tab: "Cloud Run (School Portal API)" = ₱100 / enrollment. Rounded up for contingency.
6. Compute Engine e2-standard-2 — OSRM Road Routing → Budget tab: ₱10,272 / enrollment
Inputs & Assumptions
Instance type | e2-standard-2 (2 vCPU, 8 GB RAM) |  |  | Smallest general-purpose instance with sufficient RAM to hold the Philippines OpenStreetMap road network (~3 GB) in memory without swapping.
On-demand rate (asia-southeast1) | $0.0767 / hour |  |  | Source: cloud.google.com/compute/all-pricing [Source 7]
Runtime | 90 days = 2,160 hours (enrollment window only) |  |  | Shut down off-season. No cost outside enrollment period.
Why Compute Engine — not Cloud Run | 3 GB routing graph must stay in RAM |  |  | Cloud Run scales to zero between requests, clearing the in-memory routing graph (loaded at startup: ~30–60 sec). Compute Engine keeps the instance alive 24/7, holding OSRM's pre-processed road network ready for instant queries.
Why OSRM — not Google Maps API | Saves ~₱3,100,000 per enrollment |  |  | Google Maps Distance Matrix API costs $5 per 1,000 pairs. At 1M learners × 10 school detail views = 10M pairs: $50,000 = ₱3,100,000. OSRM is open-source; the only cost is the VM instance.
Calculation
Component / Parameter | Rate | × Quantity | = USD | Notes / Source
Instance cost (on-demand) | $0.0767 / hour | 2,160 hours | $165.67 | 90 days × 24 hrs/day = 2,160 hrs × $0.0767 = $165.67 [Source 7]
Subtotal (USD) |  |  | $165.67
× ₱62 / USD = | $165.67 | ₱10,272 |  | → Budget tab: "Compute Engine e2-standard-2 (OSRM)" = ₱10,272 / enrollment
7. Cloud SQL for PostgreSQL — 2 vCPU, 7.5 GB RAM → Budget tab: ₱89,280 / year
Inputs & Assumptions
Instance spec | db-custom-2-7680 (2 vCPU, 7.5 GiB RAM) |  |  | Upgraded from 1 vCPU / 3.75 GiB (staging) to handle concurrent enrollment load. Supports ~200–400 DB writes/second sustained (~20,000–30,000 simultaneous submitting users via PgBouncer).
Edition | Enterprise — General Purpose |  |  | Default Cloud SQL edition for new instances. Source: cloud.google.com/sql/pricing [Source 3]
vCPU rate (asia-southeast1, on-demand) | $0.0578 / vCPU / hour |  |  | Enterprise Edition, General Purpose, Default (on-demand). Source: cloud.google.com/sql/pricing [Source 3]
Memory rate (asia-southeast1, on-demand) | $0.0098 / GiB / hour |  |  | Enterprise Edition, General Purpose, Default (on-demand). Source: cloud.google.com/sql/pricing [Source 3]
SSD storage rate | $0.222 / GB / month |  |  | Source: cloud.google.com/sql/pricing [Source 3]
Storage provisioned | 50 GB SSD |  |  | Sufficient for 1M student submissions + school data + audit logs for the pilot year.
Runtime | 12 months (always-on) |  |  | Student submission records must persist year-round — database cannot scale to zero. Contains all enrollment audit logs, ranked choices, and school slot data.
Derived Values (per month, 730 hours)
vCPU cost per month | $84.39 |  |  | 2 vCPU × $0.0578/hr × 730 hrs
Memory cost per month | $53.66 |  |  | 7.5 GiB × $0.0098/GiB-hr × 730 hrs
Storage cost per month | $11.10 |  |  | 50 GB × $0.222/GB-month
Total per month | $149.15 |  |  | $84.39 + $53.66 + $11.10
Calculation [Source 3: cloud.google.com/sql/pricing]
Component / Parameter | Rate | × Quantity | = USD | Notes / Source
vCPU (2 vCPU × $0.0578 × 730 hrs) | $84.39 / month | 12 months | $1,012.68 | 2 × $0.0578 × 730 = $84.39/month
Memory (7.5 GiB × $0.0098 × 730 hrs) | $53.66 / month | 12 months | $643.92 | 7.5 × $0.0098 × 730 = $53.66/month
SSD Storage (50 GB × $0.222) | $11.10 / month | 12 months | $133.20 | 50 GB × $0.222/GB/month
Subtotal (USD) |  |  | $1,789.80
× ₱62 / USD = | $1,789.80 | ₱110,968 → rounded ₱111,000 |  | → Budget tab: "Cloud SQL for PostgreSQL (2 vCPU, 7.5 GiB RAM)" = ₱111,000 / year
8. Cloud SQL Automated Backups (90-day retention) → Budget tab: ₱7,440 / year
Inputs & Assumptions
Backup storage rate | $0.08 / GB / month |  |  | Cloud SQL backup storage overage rate. Source: cloud.google.com/sql/pricing [Source 3]
Estimated backup storage at steady state | ~110 GB |  |  | 90 daily compressed snapshots × ~1 GB each + WAL (write-ahead log) for PITR. Submissions are text-heavy JSON — compress well.
Retention policy | 90 days + PITR enabled |  |  | Required for government enrollment records: covers the full enrollment window plus a post-close period for dispute resolution and audit.
Calculation
Component / Parameter | Rate | × Quantity | = USD | Notes / Source
Backup storage (90-day retention) | $0.08 / GB / month | ~110 GB × 12 months | ~$105.60 | $0.08 × 110 GB = $8.80/month × 12 = $105.60. Rounded to $10/month = $120/year for budget. [Source 3]
Subtotal (USD) |  |  | ~$120.00
× ₱62 / USD = | ~$120.00 | ₱7,440 |  | → Budget tab: "Cloud SQL Automated Backups (90-day retention)" = ₱7,440 / year
Items not detailed above (PgBouncer, Cloud Run Jobs, Cloud Storage, BigQuery, Egress/Monitoring) are estimated from official GCP pricing pages at the unit rates shown in the Budget tab Notes column. All rates are subject to change — verify on official Google Cloud pricing pages before DBM submission.